## Sheet1
Activities | Starting date | Ending date | Duration
1st supervisor meet (8/11/21)(1 day) | 2021-11-08 | 2021-11-08 | 1
Literature review (2 days) | 2021-11-09 | 2021-11-10 | 1
Review some datasets (2 days) | 2021-11-09 | 2021-11-10 | 1
Discussion about possible software (2 days) | 2021-11-09 | 2021-11-10 | 1
Title defense (11/11/21) (1day) | 2021-11-11 | 2021-11-11 | 1
Started to gain knowledge about neural networks (3 days) | 2021-11-12 | 2021-11-15 | 3
Started to gain knowledge about Gradient descent algorithm (5 days) | 2021-11-16 | 2021-11-21 | 5
Started to gain knowledge about convolutional neural networks (6 days) | 2021-11-18 | 2021-11-24 | 6
Talking about our feasible method in 2nd supervisor meet (25/11/21) (1day) | 2021-11-25 | 2021-11-25 | 1
Review the existing methods of implementation (2 days) | 2021-11-26 | 2021-11-28 | 2
Gain knowledge about LSTM (5 days) | 2021-11-28 | 2021-12-03 | 4
Gain knowledge about Bidirectional LSTM (5 days) | 2021-11-28 | 2021-12-03 | 5
Thinking feasible method about our project (5 days) | 2021-12-03 | 2021-12-08 | 5
First follow up (9/12/21) (1 day) | 2021-12-09 | 2021-12-09 | 1
Include dataset for our project (2 days) | 2021-12-10 | 2021-12-12 | 2
Separate data for training and testing (3 days) | 2021-12-12 | 2021-12-15 | 3
Train the data using training data algorithm (5 days) | 2021-12-14 | 2021-12-19 | 5
Test or predict using test data (5days) | 2021-12-14 | 2021-12-19 | 5
Result analysis (3day) | 2021-12-19 | 2021-12-22 | 3
3rd Supervisor meet (23/12/21) (1day) | 2021-12-23 | 2021-12-23 | 1
Find out the drawbacks (5days) | 2021-12-24 | 2021-12-29 | 5
Working on the drawbacks (15days) | 2021-12-30 | 2022-01-14 | 14
Fix the drawbacks and make a partially deliverable system (20days) | 2021-01-06 | 2021-01-26 | 20
Started 1st term report writing (20 days) | 2021-01-06 | 2021-01-26 | 20
Second follow up (27/01/22) (1 day) | 2022-01-27 | 2022-01-27 | 1
Continuing 1st term report writing (9 days) | 2022-01-28 | 2022-02-05 | 7
1st term report submission (06/02/22)(1 day) | 2022-02-06 | 2022-02-06 | 1
Merge First and Second follow up reviews () | 2022-02-07
Find out overall full projects drawbacks | 2022-02-07
Working on all the drawbacks | 2022-02-07
Implement project final | 2022-02-07
Prepare the Final report | 2022-02-07